## Production & Launch
Description | Date Due | Date Completed | Comments | Cost | Paid
Production
Developemtal Edit
Line Edit
Proofreading
Review of Proof |  |  | Review the proofread copy
Bowker Setup |  |  | Set up your ISBN
KDP Setup |  |  | Set up your KDP page
Interior Layout
Find cover images |  |  | Find images for print and ebook cover
Ebook Cover |  |  | Ebook cover design complete & approved
Print Cover Template |  |  | Download print cover template from KDP or Ingram
Print Cover |  |  | Finish and approve print cover design
Back Cover Text |  |  | Brief summary and bio for back cover
Files to Ingram |  |  | Upload interior and cover files to Ingram
Approve Ingram Proof
Convert to epub
Convert to mobi
Marketing Prep
Author Bio
Book summary (full length)
Log line
Identify Similar Titles and Authors |  |  | Which titles/authors do you want to target in Amazon or Facebook ads?
Add book to author site
Announce on Facebook
Add to Goodreads
Advance Copies
NetGalley
Bookish First
Excerpt for Bookish
Upload to Prolific Works
BookSirens
Editorial Reviews
Best Thrillers
Booklife/PW Reviews
Clarion Reviews
Feathered Quill
Foreward Reviews
Independent Publisher
IndieReader
Int'l Review of Books
Kirkus Review
Library Journal Review
Midwest Book Review
Readers Favorite
Contests
Booklife Prize
Writers Digest Self-Published Book Awards
Library Journal Indie eBook Awards
The Feathered Quill
Next Gen Indie Book Awards
Readers Favorite
IndieReader
Independent Publishers IPPY
National Indie Excellence Awards
Foreword Indies
IBPA Franklin Awards
Best Indie Book Award
Virginia Author Project
List of book awards
eLit Book Awards
Misc Tasks
Backmatter Links |  |  | Add new book summary and purchase links into back matter of existing books.
Post Reviews
Blog
Ingram
Amazon
Facebook
Booklife
Goodreads
Note on D71: As advance reviews come in, post review quotes to these sites.

## Paid Promo Sites
Promo Site | Date Submitted | Promo Date | Notes | Cost
Awesome Gang
Bargain Booksy
Bargin eBook Hunter
Book Adrenaline
Book Barbarian
Book Basset
Book Cave
Book Dealio
Book Goodies
Book Gorilla
Book Rebel
Book Zio
BookBub
Booklovers Heaven
Booksends
Choosy Bookworm
Digital Book Today
Early Bird Books
Ebook Soda
Ebooks Habit
Ereader IQ
Ereader News Today
Free Booksy
Free Kindle Books and Tips
Genre Pulse
Hot Zippy
Just Kindle Books
Kindle Nation Daily
Many Books
Murder & Mayhem
My Romance Reads
Mystery Reads
Pixel Scroll
Price Dropped Books
Reading Deals
Red Feather Romance
Robin Reads
The eReader Café
The Fussy Librarian
Your New Books
Looking for more? See this list of promo sites.
Note on B1: On which date did you fill out the submission form to buy this promo?
Note on C1: If your promo was approved, on which date will it run?
Note on D1: Keep track of which promo option you chose, whether you were rejected, whether you need to submit additional materials, etc.